## Project Meets
Atharva Shah - Scrum Master's Log for WYDRN Project
Members x Task Assigned | 15th July '22 | 20th July '22 | 24th July '22 | 27th July '22 | 3rd August '22 | 8th August '22 | 23rd August '22 | 3rd September '22 | 8th September'22
Om Khulbe | Discussed and showcased project ideas, implementation, tech stack. Scrum master gave a walkthrough of all the features and functionalities. | Inquired about areas of interest that suits to their development style. Assigned general roles and responsibilities. | ⌛ Task #1 Assigned: Designing and Coding of Landing Page. Page will be static and made using HTML, Bootstrap CSS and JS for Responsiveness. References provided by Scrum Master. | Reported as working on Task #1 | Reported as Task #1 30% done | Reported as Task #1 50% done | Draft is reported as ready. I reviewed it and passed it. Final view will be ready soon. | ✅ TASK #1 Completed. ⌛ Task #2 assigned - Adding icons, adding more styling sections and designing header. | Working on Task #2
Anay Deshpande | Discussed and showcased project ideas, implementation, tech stack. Scrum master gave a walkthrough of all the features and functionalities. | Inquired about areas of interest that suits to their development style. Assigned general roles and responsibilities. | ⌛ Task #1 Assigned: Creating of user Flow Chart for WYDRN diagram. Initial diagram layout provided by Scrum Master. | ✅ TASK #1 Completed | ⌛ Task #2 Assigned: Writing Basic SQL queries for "stats.php" page. 50% of the code with references provided by Scrum Master. Designing tables for admin page and extending CSS code provided by Scrum Master. | ✅ TASK #2 Completed. ⌛ Task #3 assigned - writing test case for each page. | Working on Multiple mini-tasks assigned. Entire list here - https://atharvashah.notion.site/TaskList-for-Anay-5657133ae92a4b0c83a0b844ad6a7904 | ⌛ Task #4 assigned - adding meta tags, collecting videos, adding voiceover to import/export walkthroughs and badges backend assistance. TASK #3 partially done. | ✅ TASK #4 Completed. Task 3 ongoing
Lavesh Milani | Discussed and showcased project ideas, implementation, tech stack. Scrum master gave a walkthrough of all the features and functionalities. | Inquired about areas of interest that suits to their development style. Assigned general roles and responsibilities. | ⌛ Task #1 Assigned: Creating of ML Models related to 5 Medias. Python Boilerplate provided by Scrum Master along with detailed implementation strategies. | Reported as working on Task #1 | Reported as working on Task #1 | Reported as working on Task #1 | Reported as working on Task #1. Minor delay as per the expected deadline | Resolved some issues on a meet with the Scrum Master regarding technical hindrances. | Reported as working on Task #1. Minor delay as per the expected deadline
Atharva Shirukar | Discussed and showcased project ideas, implementation, tech stack. Scrum master gave a walkthrough of all the features and functionalities. | Inquired about areas of interest that suits to their development style. Assigned general roles and responsibilities. | ⌛ Task #1 Assigned: Documentation work assigned. Initial layout sketched by Scrum Master provided by Scrum Master. | Reported as working on Task #1 | Reported as Task #1 50% done | ✅ TASK #1 Completed. ⌛Task #2 assigned: Collection of member bios and executing test case for each page. | ✅ Task #2 completed. ⌛ TASK #3 Documentation Work Assigned. | ✅ Task #3 completed. ⌛ TASK #4 assigned - help with White Box testing and provide feedback for UI/UX improvements | Working on Task #4
Nikhil Haswani | Discussed and showcased project ideas, implementation, tech stack. Scrum master gave a walkthrough of all the features and functionalities. | Inquired about areas of interest that suits to their development style. Assigned general roles and responsibilities. | ⌛ Task #1 Assigned: To assist in documenation and image collection process. | Reported as working on Task #1 | Reported as working on Task #1 | ✅ TASK #1 Completed. ⌛Task #2 assigned: Reaching out to other Scrum masters and reporting interested parties for beta testing. Find Book Images | ⌛ TASK #3 Documentation Work Assigned. Task #2 on hold for now. | Working on Task #3 | Task #3 50% completed
Rashmi Kamble | Discussed and showcased project ideas, implementation, tech stack. Scrum master gave a walkthrough of all the features and functionalities. | Inquired about areas of interest that suits to their development style. Assigned general roles and responsibilities. | ⌛ Task #1 Assigned: To collected 75 image artifacts relevant to the site. Detailed instructions on resolution, category, etc provided by Scrum Master. | Reported as working on Task #1 | Reported as working on Task #1 | ✅ TASK #1 Completed. ⌛Task #2 assigned: Populating quotes.php with pop culture content. | ✅ TASK #2 Completed. ⌛ TASK #3 Documentation Work Assigned. | Working on Task #3 | Task #3 % 75% completed