## PROJECT DETAILS
PROJECT NUMBER | GROUP A
PROJECT NAME | WYDRN
PROJECT MANAGER | ATHARVA SHAH
DATE | 25th August 2022
VERSION | Pre-Release

## USER STORIES
WYDRN - AGILE USER STORY
USER STORY ID | PRIORITY | AS A [type of user] | I NEED TO [do some task] | SO THAT I CAN [get some result] | Status
| High | Administrator | View Site Stats | Get an overview of registered members, logged activity and rate at which the web app is scaling | Completed
| High | Administrator | Moderate Users | View their profile pic, delete their account or check their stats | Completed
| High | Guest | View the home page | Visit the signup page and the homepage | Completed
| Low | Guest | View privacy and policy page | Read the privacy policy before creating an account | Completed
| Medium | Guest | View about us page | View the bios and contribution of the development team towards the project | Completed
| High | Guest | Sign up. | Become a member and sign in later | Completed
| High | Member | Sign in to my account | View profile and access all the site features | Completed
|  | Member | Edit Profile Pic | Update and upload my profile picture.
|  | Member | Edit Background Image | Upload or update my background image.
| Medium | Member | Search/Browse a Book | View the cover and other metadata like Author, Release Year and Genre | Completed
| Medium | Member | Search/Browse a Movie | View the cover and other metadata like Language, Release Year and Genre | Completed
| Medium | Member | Search/Browse a TV Show | View the cover and other metadata like Air Date and No. of episodes | Completed
| Medium | Member | Search/Browse a Videogame | View the cover and other metadata like Publisher, Genre and Release Year | Completed
| Medium | Member | Search/Browse a Album | View the cover and other metadata like Artist and Genre | Completed
| High | Member | Add currently playing Videogame | Keep a track of games i've played so far. | Completed
| High | Member | Add currently listening to Music | Keep a track of Music i've listened to so far. | Completed
| High | Member | Add currently reading Book | Keep a track of books i've read so far. | Completed
| High | Member | Add currently watching Movie | Keep a track of movies i've watched so far. | Completed
| High | Member | Add currently watching TV Show | Keep a track of TV showsi've watched so far. | Completed
|  | Member | Search for other users | Find other members and view their profiles and follow them. | Completed
| High | Member | Click on Mutual Media on a user's profile page | View common media items like videogames, tv shows, movies, books and music that I share with them. | Completed
| High | Member | Follow other users | get an update about new music, books, videogames , movies & TV shows that other members might be into and post about. | Completed
| High | Member | Get followed by other users | make everyone see about the what new activity i'm up to. | Completed
| Medium | Member | Unfollow users | Remove other users from my following list | Completed
| Medium | Member | View Stats | View their stats for every media added by them. | Completed
| Medium | Member | Clear activity status. | Clear the current activity status | Completed
| Low | Member | Get badges based on activity count |  | Completed
| Low | Member | Get badges based on follower count |  | Completed
| Low | Member | Filter by date on diary page | Visit specific date to view my activity. | Completed
| Medium | Member | Export Activity data to pdf | Export data as PDF | Completed
| Low | Member | Export Activity data to csv | Export data as CSV | Completed
| Medium | Member | Import Activity from csv | Import data from CSV | Completed
| High | Member | View my profile and activity details | Displays profile acticities such as followers, following count, etc. | Completed
| Medium | Member | View Social Feed | View chronological activities of followed users. | Completed
| Medium | Member | Click on books under Media Dropdown | View my added books in a Grid/List fashion | Completed
| Medium | Member | Click on movies under Media Dropdown | View my added movies a Grid/List fashion | Completed
| Medium | Member | Click on video games under Media Dropdown | View my added video games a Grid/List fashion | Completed
| Medium | Member | Click on TV show under Media Dropdown | View my added TV shows a Grid/List fashion | Completed
| Medium | Member | Click on albums under Media Dropdown | View my added albums a Grid/List fashion | Completed
| Low | Member | Verify my email | Be a verified user. | Completed
| Low | Member | Delete Account | Wipe my data from the system permanently | Completed
| High | Member | Clear my profile | Clear my activity details such as listening activity, reading activity etc. | Completed
| Medium | Member | Click on Forgot Password | Recieve a password reset link on my Email Address | Completed
| Low | Member | Click on trashcan icon on Media->Books page while hovering on a book cover | To permanently delete the book as well as any previous entries of the book from my account. | Completed
| Low | Member | Click on trashcan icon on Media->Movies page while hovering on a movie cover | To permanently delete the movie as well as any previous entries of the movie from my account. | Completed
| Low | Member | Click on trashcan icon on Media->TV page while hovering on a TV cover | To permanently delete the TV as well as any previous entries of the TV from my account. | Completed
| Low | Member | Click on trashcan icon on Media->Videogame page while hovering on a Videogame cover | To permanently delete the Videogame as well as any previous entries of the Videogame from my account. | Completed
| Low | Member | Click on trashcan icon on Media->Album page while hovering on a Album cover | To permanently delete the Album as well as any previous entries of the Album from my account. | Completed
| Low | Member | Click on Bell Icon Besides my Profile | Get notified about my new followers | Completed

## PROJECT BACKLOG
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS
1 | Backend for Admin Page |  | Anay Deshpande + Atharva Shah | 2022-05-08 | 13/08/2022 |  |  | High | Complete | 5
2 | Frontend for Admin Page |  | Atharva Shah | 25/07/2022 | 27/08/2022 |  |  | Medium | Complete | 5
3 | Backend for Badges Page |  | Atharva Shah + Anay Deshpande | 28/08/2022 | 2022-05-09 |  |  | Medium | Complete | 2
4 | Frontend for Badges Page |  | Atharva Shah | 28/08/2022 | 2022-05-09 |  |  | Low | Complete | 4
5 | Backend for Diary Page |  | Anay Deshpande + Atharva Shah | 22/07/2022 | 23/09/2022 |  |  | High | Complete | 3
6 | Frontend for Diary Page |  | Atharva Shah | 25/07/2022 | 27/08/2022 |  |  | High | Complete | 4
7 | Backend for Deleting User |  | Atharva Shah | 2022-05-08 | 2022-08-08 |  |  | Medium | Complete | 1
8 | Backend for Edit Profile |  | Atharva Shah | 19/07/2022 | 25/08/2022 |  |  | High | Complete | 4
9 | Frontend for Edit Profile |  | Atharva Shah | 27/07/2022 | 25/08/2022 |  |  | Medium | Complete | 3
1 | Backend for Feed Page |  | Atharva Shah | 28/07/2022 | 2022-03-08 |  |  | High | Complete | 3
11 | Frontend for Feed Page |  | Atharva Shah | 2022-03-07 | 2022-05-09 |  |  | High | Complete | 4
12 | Backend for Follow Function |  | Atharva Shah | 2022-05-08 | 13/08/2022 |  |  | Medium | Complete | 1
13 | Backend for Followers Page |  | Atharva Shah | 2022-02-08 | 16/08/2022 |  |  | High | Complete | 2
14 | Frontend for Followers Page |  | Atharva Shah | 15/08/2022 | 29/08/2022 |  |  | Medium | Complete | 2
15 | Backend for Following Page |  | Atharva Shah | 2022-02-08 | 16/08/2022 |  |  | High | Complete | 2
16 | Frontend for Following Page |  | Atharva Shah | 15/08/2022 | 29/08/2022 |  |  | Medium | Complete | 2
17 | Making a multi-purpose Functions file for all pages |  | Atharva Shah | 17/08/2022 | 2022-03-09 |  |  | High | Complete | 10
18 | Making 4 multi-purpose Header files for all pages |  | Atharva Shah | 22/07/2022 | 2022-02-09 |  |  | High | Complete | 5
19 | Frontend Design and Code for Header/Navbar |  | Atharva Shah | 25/07/2022 | 2022-04-08 |  |  | Medium | Complete | 2
2 | Backend for Login and Signup Page |  | Atharva Shah | 15/07/2022 | 2022-11-08 |  |  | High | Complete | 1
21 | Frontend for Login and Signup Page |  | Atharva Shah | 2022-12-08 | 2022-05-09 |  |  | Medium | Complete | 5
22 | Backend for Logout Function |  | Atharva Shah | 15/08/2022 | 21/08/2022 |  |  | Medium | Complete | 1
23 | Backend for Your Media Books Page |  | Atharva Shah | 2022-02-08 | 2022-02-09 |  |  | High | Complete | 4
24 | Frontend for Your Media Books Page |  | Atharva Shah | 23/08/2022 | 2022-05-09 |  |  | Medium | Complete | 6
25 | Backend for Your Media Movies Page |  | Atharva Shah | 2022-04-08 | 2022-05-09 |  |  | High | Complete | 4
26 | Frontend for Your Media Movies Page |  | Atharva Shah | 25/08/2022 | 2022-04-09 |  |  | Medium | Complete | 6
27 | Backend for Your Media TV Page |  | Atharva Shah | 2022-03-08 | 2022-03-09 |  |  | High | Complete | 4
28 | Frontend for Your Media TV Page |  | Atharva Shah | 25/08/2022 | 31/08/2022 |  |  | Medium | Complete | 6
29 | Backend for Your Media Videogames Page |  | Atharva Shah | 2022-03-08 | 2022-03-09 |  |  | High | Complete | 4
3 | Frontend for Your Media Videogames Page |  | Atharva Shah | 23/08/2022 | 2022-05-09 |  |  | Medium | Complete | 6
31 | Backend for Your Media Music Page |  | Atharva Shah | 2022-02-08 | 2022-02-09 |  |  | High | Complete | 4
32 | Frontend for Your Media Music Page |  | Atharva Shah | 25/08/2022 | 2022-04-09 |  |  | Medium | Complete | 6
33 | Backend for Your Media List View Page |  | Atharva Shah | 2022-04-08 | 2022-05-09 |  |  | High | Complete | 3
34 | Frontend for Your Media List View Page |  | Atharva Shah | 25/08/2022 | 2022-04-09 |  |  | Medium | Complete | 2
35 | Frontend for Privacy Policy Page |  | Atharva Shah | 16/07/2022 | 2022-02-08 |  |  | High | Complete | 1
36 | Animation for Landing Page |  | Anay Deshpande | 2022-02-07 | 2022-01-09 |  |  | Medium | Complete | 2
37 | Finalization of Landing Page |  | Atharva Shah | 16/07/2022 | 2022-05-09 |  |  | High | Complete | 3
38 | Design and Code for Landing Page |  | Om Khulbe | 16/07/2022 | 2022-03-08 |  |  | Medium | Complete | 5
39 | Backend for Profile Page |  | Atharva Shah | 2022-02-07 | 2022-02-08 |  |  | High | Complete | 1
4 | Frontend for Profile Page |  | Atharva Shah | 2022-03-07 | 21/08/2022 |  |  | Medium | Complete | 3
41 | Backend for Password Reset Page |  | Atharva Shah | 2022-09-08 | 27/08/2022 |  |  | Medium | Complete | 3
42 | Frontend for Password Reset Page |  | Atharva Shah | 15/08/2022 | 31/08/2022 |  |  | Medium | Complete | 1
43 | SMTP Email Config and Setup for Password Reset and Account Verification |  | Atharva Shah | 2022-09-08 | 27/08/2022 |  |  | High | Complete | 1
44 | Backend for Verify Email |  | Atharva Shah | 15/08/2022 | 31/08/2022 |  |  | Medium | Complete | 3
45 | Frontend for Verify Email |  | Atharva Shah | 25/08/2022 | 31/08/2022 |  |  | Medium | Complete | 2
46 | Backend for Search users Page |  | Atharva Shah | 2022-03-07 | 2022-02-08 |  |  | High | Complete | 2
47 | Frontend for Search Users Page |  | Atharva Shah | 16/08/2022 | 2022-05-09 |  |  | Medium | Complete | 2
48 | Backend for Leaderboard Widgets |  | Atharva Shah | 21/08/2022 | 2022-01-09 |  |  | Low | Complete | 1
49 | Frontend for Leaderboard Widgets |  | Atharva Shah | 31/08/2022 | 2022-06-09 |  |  | Low | Complete | 2
5 | Backend for Stats Page |  | Anay Deshpande + Atharva Shah | 2022-09-08 | 27/08/2022 |  |  | High | Complete | 1
51 | Frontend for Stats Page |  | Anay Deshpande + Atharva Shah | 25/08/2022 | 31/08/2022 |  |  | Medium | Complete | 2
52 | Frontend for About Page |  | Anay Deshpande + Atharva Shah | 2022-03-07 | 2022-02-08 |  |  | High | Complete | 3
53 | Frontend for 44 Error Page |  | Atharva Shah | 2022-03-07 | 2022-02-08 |  |  | High | Complete | 1
54 | Configuration of HTACCESS file |  | Atharva Shah | 16/07/2022 | 2022-03-08 |  |  | Medium | Complete | 1
55 | Frontend for Import/Export Page |  | Atharva Shah | 16/08/2022 | 2022-05-09 |  |  | High | Complete | 4
56 | Backend for CSV Export Page |  | Atharva Shah | 21/08/2022 | 2022-01-09 |  |  | High | Complete | 3
57 | Frontend for CSV Export Page |  | Atharva Shah | 29/08/2022 | 2022-06-09 |  |  | Medium | Complete | 2
58 | Backend for CSV Import Page |  | Atharva Shah | 21/08/2022 | 2022-01-09 |  |  | High | Complete | 6
59 | FrontEnd for CSV Import Page |  | Atharva Shah | 31/08/2022 | 2022-06-09 |  |  | Medium | Complete | 2
6 | Dynamic Export PDF Generation |  | Atharva Shah | 2022-03-08 | 2022-04-09 |  |  | High | Complete | 4
61 | Backend for Browse Books Page |  | Atharva Shah | 2022-03-07 | 2022-05-08 |  |  | High | Complete | 4
62 | Frontend for Browse Books Page |  | Atharva Shah | 27/08/2022 | 2022-05-09 |  |  | Medium | Complete | 6
63 | Backend for Browse Movies Page |  | Atharva Shah | 31/07/2022 | 2022-07-08 |  |  | High | Complete | 4
64 | Frontend for Browse Movies Page |  | Atharva Shah | 26/08/2022 | 2022-05-09 |  |  | Medium | Complete | 6
65 | Backend for Browse TV Page |  | Atharva Shah | 2022-03-07 | 2022-08-08 |  |  | High | Complete | 4
66 | Frontend for Browse TV Page |  | Atharva Shah | 27/08/2022 | 2022-05-09 |  |  | Medium | Complete | 6
67 | Backend for Browse Videogames Page |  | Atharva Shah | 29/07/2022 | 2022-07-08 |  |  | High | Complete | 4
68 | Frontend for Browse Videogames Page |  | Atharva Shah | 26/08/2022 | 2022-05-09 |  |  | Medium | Complete | 6
69 | Backend for Browse Music Page |  | Atharva Shah | 21/08/2022 | 2022-05-09 |  |  | High | Complete | 4
7 | Frontend for Browse Music Page |  | Atharva Shah | 31/08/2022 | 2022-05-09 |  |  | Medium | Complete | 6
71 | Applying for Google Books API |  | Atharva Shah | 15/07/2022 | 24/08/2022 |  |  | High | Complete | 1
72 | Applying for LastFM API |  | Atharva Shah | 15/07/2022 | 2022-02-08 |  |  | High | Complete | 1
73 | Applying for TMDB API |  | Atharva Shah | 15/07/2022 | 28/08/2022 |  |  | High | Complete | 1
74 | Applying for RAWG API |  | Atharva Shah | 15/07/2022 | 2022-03-08 |  |  | High | Complete | 1
75 | Integrating Google Books API into the application |  | Atharva Shah | 2022-02-08 | 21/08/2022 |  |  | High | Complete | 2
76 | Integrating LastFM API into the application |  | Atharva Shah | 2022-02-08 | 21/02/2022 |  |  | High | Complete | 2
77 | Integrating TMDB API into the application |  | Atharva Shah | 2022-02-08 | 21/02/2022 |  |  | High | Complete | 2
78 | Integrating RAWG API into the application |  | Atharva Shah | 2022-02-08 | 21/02/2022 |  |  | High | Complete | 2
79 | Backend for Adding Activity (Welcome.php and WYDRN.php) |  | Atharva Shah | 17/07/2022 | 2022-11-08 |  |  | Medium | Complete | 1
80 | Frontend for Adding Activity (Welcome.php and WYDRN.php) |  | Atharva Shah | 2022-03-07 | 2022-01-08 |  |  | Medium | Complete | 1
81 | Gather Templates for Documentation Team |  | Atharva Shah | 17/08/2022 | 18/08/2022 |  |  | Low | Complete | 1
82 | Project Presentation |  | Nikhil Haswani + Atharva Shah + Atharva Shiurkar | 23/08/2022 | 31/08/2022 |  |  | Medium | Complete | 5
83 | Agile User Stories |  | Nikhil Haswani + Rashmi Kamble | 2022-03-09 | 2022-04-09 |  |  | Low | Complete | 2
84 | Agile Project Backlog |  | Atharva Shah + Rashmi Kamble | 2022-08-09 | 2022-09-09 |  |  | Low | Complete | 2
85 | Maintaining Meeting Log |  | Atharva Shah | 15/07/2022 |  |  |  | Medium | Complete | 2
86 | Testing Matrix |  | Anay Deshpande | 2022-11-08 | 29/08/2022 |  |  | High | Complete | 2
87 | General Unit Testing |  | Anay Deshpande | 2022-11-08 | 29/08/2022 |  |  | High | Complete | 2
88 | Peer Review Co-Ordination |  | Nikhil Haswani | 2022-02-08 | 31/08/2022 |  |  | Medium | Complete | 1
89 | Black Box Testing |  | Nikhil Haswani + Lavesh Milani | 2022-02-08 | 21/08/2022 |  |  | High | Complete | 3
90 | White Box Testing |  | Anay Deshpande + Om Khulbe | 2022-06-08 | 2022-01-09 |  |  | High | Complete | 7
91 | Project Diagrams (ERD, DFD and Flow Diagram) |  | Anay Deshpande | 16/08/2022 | 19/08/2022 |  |  | Medium | Complete | 8
92 | Database Schema Design |  | Anay Deshpande + Atharva Shah | 16/08/2022 | 19/08/2022 |  |  | Medium | Complete | 5
93 | Database Weekly Exports and maintainence |  | Atharva Shah | 15/07/2022 |  |  |  | High | Complete | 1
94 | Setup Version Control Using Git |  | Atharva Shah | 17/07/2022 | 2022-11-08 |  |  | High | Complete | 2
95 | Collection of Member Bios |  | Atharva Shiurkar | 2022-11-08 | 29/08/2022 |  |  | Medium | Complete | 1
96 | Collection of Quotes |  | Rashmi Kamble | 2022-05-08 | 2022-08-08 |  |  | Low | Complete | 2
97 | Collection of Images |  | Rashmi Kamble | 2022-05-08 | 2022-08-08 |  |  | Low | Complete | 2
98 | Collection of Icons |  | Om Khulbe + Atharva Shah | 2022-07-08 | 2022-08-08 |  |  | Low | Complete | 2
99 | Designing of Badges |  | Atharva Shah | 2022-01-09 | 2022-04-09 |  |  | Low | Complete | 2
1 | Collection of Videos |  | Anay Deshpande | 2022-03-08 | 2022-05-09 |  |  | Low | Complete | 2
11 | Adding Narration to Import Walkthrough Videos |  | Anay Deshpande | 2022-03-08 | 2022-05-09 |  |  | Medium | Complete | 3
12 | Recording Import Wallkthrough Videos |  | Atharva Shah | 2022-03-08 | 2022-02-09 |  |  | Medium | Complete | 2
13 | Writing Python ML Model for Movie Recommendation |  | Atharva Shah | 2022-11-08 | 29/08/2022 |  |  | High | Complete | 5
15 | Movie Recommendation Front-End |  | Atharva Shah | 23/08/2022 | 2022-02-09 |  |  | Medium | Complete | 2
16 | Writing Python ML Model for Book Recommendation |  | Lavesh Milani | 21/08/2022 | 2022-05-09 |  |  | High | Complete | 5
18 | Book Recommendation Front-End |  | Atharva Shah | 29/08/2022 | 2022-02-09 |  |  | Medium | Complete | 2
19 | Writing Python ML Model for TV Recommendation |  | Atharva Shah | 21/08/2022 | 2022-05-09 |  |  | High | Complete | 5
111 | TV Recommendation Front-End |  | Atharva Shah | 21/08/2022 | 2022-05-09 |  |  | Medium | Complete | 2
112 | Writing Python ML Model for Videogame Recommendation |  | Atharva Shah | 23/08/2022 | 2022-02-09 |  |  | High | Complete | 5
114 | Videogame Recommendation Front-End |  | Atharva Shah | 19/08/2022 | 31/08/2022 |  |  | Medium | Complete | 2
115 | Writing Python ML Model for Music Recommendation |  | Atharva Shah | 21/08/2022 | 2022-05-09 |  |  | High | Complete | 5
117 | Music Recommendation Front-End |  | Atharva Shah | 29/08/2022 | 2022-06-09 |  |  | Medium | Complete | 2
118 | Integrating all 5 ML Models and Integrating them with the Front-End |  | Atharva Shah | 21/08/2022 |  |  |  | Medium | Complete | 1
119 | Adding Delete Book Item Backend Functionality |  | Atharva Shah | 2022-01-09 | 2022-11-09 |  |  | Low | Complete | 1
12 | Adding Delete Movie Item Backend Functionality |  | Atharva Shah | 18/09/2022 | 19/09/2022 |  |  | Low | Complete | 1
121 | Adding Delete TV Item Backend Functionality |  | Atharva Shah | 18/09/2022 | 19/09/2022 |  |  | Low | Complete | 1
122 | Adding Delete Music Item Backend Functionality |  | Atharva Shah | 18/09/2022 | 19/09/2022 |  |  | Low | Complete | 1
123 | Adding Delete Videogame Item Backend Functionality |  | Atharva Shah | 18/09/2022 | 19/09/2022 |  |  | Low | Complete | 1
124 | Backend for Notifications Page |  | Atharva Shah | 18/09/2022 | 19/09/2022 |  |  | Medium | Complete | 2
125 | Frotend for Notifications Page |  | Atharva Shah | 18/09/2022 | 19/09/2022 |  |  | Low | Complete | 1
126 | Updating Documentation Images |  | Atharva Shiurkar |  |  |  |  | Low | Complete | 3
127 | Updating Icons with better ones |  | Anay Deshpande | 15/09/2022 | 15/09/2022 |  |  | Low | Complete | 2
128 | Provide insightful tips on improving design and back-end logic. |  | Anay Deshpande |  |  |  |  | High | Complete | 2
129 | Assist in pagination |  | Anay Deshpande |  |  |  |  | Low | Complete | 1
130 | Improve headings for all the pages |  | Anay Deshpande + Atharva Shah |  |  |  |  | Low | Complete | 2
131 | Made youtube thumbnails, gave voiceover, edited and uploaded tutorials |  | Anay Deshpande |  |  |  |  | Medium | Complete | 3
132 | Downloaded and edited login page background videos |  | Anay Deshpande |  |  |  |  | Medium | Complete | 1
133 | Created 2 backup APIs |  | Anay Deshpande |  |  |  |  | Low | Complete | 2
134 | Added meta keywords & description to all HTML pages |  | Anay Deshpande
135 | Designed numbers for search search page |  | Anay Deshpande
136 | Searched and updated backgrounds for all the pages |  | Anay Deshpande