## Project Meets
Atharva Shah - Scrum Master's Log for WYDRN Project
Members x Task Assigned | 15th July '22 | 20th July '22 | 24th July '22 | 27th July '22 | 3rd August '22 | 8th August '22 | 23rd August '22 | 3rd September '22 | 8th September'22 | 15th Sepmber '22 | 21st September '22 | 28th September'22
Om Khulbe | PRESENT Discussed and showcased project ideas, implementation, tech stack. Scrum master gave a walkthrough of all the features and functionalities. | PRESENT :Inquired about areas of interest that suits to their development style. Assigned general roles and responsibilities. | PRESENT : ⌛ Task #1 Assigned: Designing and Coding of Landing Page. Page will be static and made using HTML, Bootstrap CSS and JS for Responsiveness. References provided by Scrum Master. | ABSENT: Reported as working on Task #1 | ABSENT: Reported as Task #1 30% done | PRESENT : Reported as Task #1 50% done | PRESENT : Draft is reported as ready. I reviewed it and passed it. Final view will be ready soon. | PRESENT : ✅ TASK #1 Completed. ⌛ Task #2 assigned - Adding icons, adding more styling sections and designing header. | PRESENT : Working on Task #2 | PRESENT : Working on Task #2 | ABSENT: Working on Task #2 | PRESENT: Finished Task #2
Anay Deshpande | PRESENT: Discussed and showcased project ideas, implementation, tech stack. Scrum master gave a walkthrough of all the features and functionalities. | PRESENT: Inquired about areas of interest that suits to their development style. Assigned general roles and responsibilities. | PRESENT: ⌛ Task #1 Assigned: Creating of user Flow Chart for WYDRN diagram. Initial diagram layout provided by Scrum Master. | PRESENT: ✅ TASK #1 Completed | ⌛ Task #2 Assigned: Writing Basic SQL queries for "stats.php" page. 50% of the code with references provided by Scrum Master. Designing tables for admin page and extending CSS code provided by Scrum Master. | PRESENT: ✅ TASK #2 Completed. ⌛ Task #3 assigned - writing test case for each page. | PRESENT: Working on Multiple mini-tasks assigned. Entire list here - https://atharvashah.notion.site/TaskList-for-Anay-5657133ae92a4b0c83a0b844ad6a7904 | PRESENT: ⌛ Task #4 assigned - adding meta tags, collecting videos, adding voiceover to import/export walkthroughs and badges backend assistance. TASK #3 partially done. | PRESENT: ✅ TASK #4 Completed. Task 3 ongoing | PRESENT | PRESENT | PRESENT: ✅ Finished several front-end related tasks
Lavesh Milani | PRESENT: Discussed and showcased project ideas, implementation, tech stack. Scrum master gave a walkthrough of all the features and functionalities. | PRESENT: Inquired about areas of interest that suits to their development style. Assigned general roles and responsibilities. | PRESENT: ⌛ Task #1 Assigned: Creating of ML Models related to 5 Medias. Python Boilerplate provided by Scrum Master along with detailed implementation strategies. | PRESENT: Reported as working on Task #1 | PRESENT: Reported as working on Task #1 | PRESENT: Reported as working on Task #1 | PRESENT: Reported as working on Task #1. Minor delay as per the expected deadline | PRESENT: Resolved some issues on a meet with the Scrum Master regarding technical hindrances. | PRESENT: Reported as working on Task #1. Minor delay as per the expected deadline | ABSENT | ABSENT | ✅ PRESENT: Finsihed Task #1
Atharva Shirukar | PRESENT: Discussed and showcased project ideas, implementation, tech stack. Scrum master gave a walkthrough of all the features and functionalities. | PRESENT: Inquired about areas of interest that suits to their development style. Assigned general roles and responsibilities. | PRESENT: ⌛ Task #1 Assigned: Documentation work assigned. Initial layout sketched by Scrum Master provided by Scrum Master. | PRESENT: Reported as working on Task #1 | PRESENT: Reported as Task #1 50% done | PRESENT: ✅ TASK #1 Completed. ⌛Task #2 assigned: Collection of member bios and executing test case for each page. | PRESENT: ✅ Task #2 completed. ⌛ TASK #3 Documentation Work Assigned. | PRESENT: ✅ Task #3 completed. ⌛ TASK #4 assigned - help with White Box testing and provide feedback for UI/UX improvements | PRESENT: Working on Task #4 | ABSENT | PRESENT | ✅ PRESENT: Finsihed Task #4
Nikhil Haswani | PRESENT: Discussed and showcased project ideas, implementation, tech stack. Scrum master gave a walkthrough of all the features and functionalities. | PRESENT: Inquired about areas of interest that suits to their development style. Assigned general roles and responsibilities. | PRESENT: ⌛ Task #1 Assigned: To assist in documenation and image collection process. | PRESENT: Reported as working on Task #1 | PRESENT: Reported as working on Task #1 | PRESENT: ✅ TASK #1 Completed. ⌛Task #2 assigned: Reaching out to other Scrum masters and reporting interested parties for beta testing. Find Book Images | PRESENT: ⌛ TASK #3 Documentation Work Assigned. Task #2 on hold for now. | PRESENT: Working on Task #3 | PRESENT: Task #3 50% completed | PRESENT | PRESENT | ✅ PRESENT: Finsihed Task #3
Rashmi Kamble | PRESENT: Discussed and showcased project ideas, implementation, tech stack. Scrum master gave a walkthrough of all the features and functionalities. | PRESENT: Inquired about areas of interest that suits to their development style. Assigned general roles and responsibilities. | PRESENT: ⌛ Task #1 Assigned: To collected 75 image artifacts relevant to the site. Detailed instructions on resolution, category, etc provided by Scrum Master. | PRESENT: Reported as working on Task #1 | PRESENT: Reported as working on Task #1 | PRESENT: ✅ TASK #1 Completed. ⌛Task #2 assigned: Populating quotes.php with pop culture content. | PRESENT: ✅ TASK #2 Completed. ⌛ TASK #3 Documentation Work Assigned. | PRESENT: Working on Task #3 | PRESENT: Task #3 % 75% completed | ABSENT | PRESENT | ✅ PRESENT: Finsihed Task #3